EXHIBIT C

IMPLEMENTATION SCHEDULE

Land-for-Land Exchange

| Case Name: XXXXX Land Exchange Action Item Feasibility Analysis (Items 1-9) | Responsible for Preparation |  | Responsible for Costs |  | Target Date |
| --- | --- | --- | --- | --- | --- |
| 1. Exchange Proposal - Define the Estates | NFP/Forest |  |  |  |  |
| 2. Forest Plan Compliance Review/Public Benefits Summary | Forest/Zone |  |  |  |  |
| 3. Field inspections of properties + prepare Certificates of Possession | Forest/Zone/NFP |  |  |  |  |
| 4. Obtain Title Insurance Commitment | NFP/Zone | NFP |  |  |  |
| 5. Boundary Management Review | ForestSurveyor |  |  |  |  |
| 6. Federal Land Status Report | Forest/Zone |  |  |  |  |
| 7a. Water Rights Analysis | Forest/Zone |  |  |  |  |
| 7b. Wetland/Floodplain Analysis (preliminary) | Forest |  |  |  |  |
| 8. Valuation Consultation | RAT |  |  |  |  |
| 9. Identify party responsible for costs | NFP/Forest/Zone |  |  |  |  |
| 10. Draft ATI & Exhibits | Zone |  |  |  |  |
| 11. Oversight (FA and Draft ATI) | RO | RO |  |  |  |
| 12. Execute Agreement to Initiate (ATI) | NFP/Forest/RO | NFP/Forest/RO |  |  |  |
| 13. Request BLM Serialization/Segregation | Zone |  |  |  |  |
| 14. Prepare Notice of Exchange Proposal (NOEP) | Zone |  |  |  |  |
| 15. Publish NOEP for 4 weeks | Zone | NFP |  |  |  |
| 16. Notify County Commissioners, State Clearinghouse, Congressional Delegations, Tribal Governments, and other Agencies | Zone |  |  |  |  |
| 17. Submit Notice of Publication for 30 day Appropriation Committee Review | Zone/RO |  |  |  |  |
| 18. Notify Permittees | Zone |  |  |  |  |
| 19. Initiate Public Scoping | Forest |  |  |  |  |
| 20. Request Land Surveys (BLM/Forest Service) | Zone/Forest | NFP (non-Fed lands) |  |  |  |
| 21. Request Withdrawal Revocation | Zone |  |  |  |  |
| 22. Prepare draft Certificate of Use and Consent | Zone |  |  |  |  |
| 23. Request Appraisals | Zone/RAT + NFP (if NFP contract) |  |  |  |  |
| 24. Prepare Mineral Potential Report | RMET |  |  |  |  |
| 25. Request BLM Concurrence on Minerals | RMET |  |  |  |  |

| Case Name: XXXXX Land Exchange Action Items | Responsible for Preparation | Responsible for Costs | Target Date |  |  |
| --- | --- | --- | --- | --- | --- |
| 26. Complete hazmat All Appropriate Inquiry process (a) Phase I (site assessment) (b) Phase II (sampling) (c) Remediation (clean up) (d) Review by USFS (e) State concurrence (if TFGO involved) (f) Indemnification language for deeds/patent (g) Phase I update (h) Review of update by USFS | (a) NFP (b) NFP (c) NFP (d) Reg. Envir. Eng. (e) Zone (f) Zone/Reg. Env. Engineer/OGC (g) NFP (h) Reg. Env. Eng. | (a) (b) (c) NFP (d) (e) (f) (g) (h) | (a) (b) (c) (d) (e) (f) (g) (h) |  |  |
| 27. Obtain SHPO Concurrence |  |  |  |  |  |
| 28. Prepare TES Report/Consultation |  |  |  |  |  |
| 29. Finalize Wetlands/Floodplains Report |  |  |  |  |  |
| 30. Analyze Effects on Cost Share Agreements | Zone |  |  |  |  |
| 31. Prepare appropriate NEPA documentation |  |  |  |  |  |
| 32. FS review NEPA documentation (if contracted) | Forest |  |  |  |  |
| 33. NEPA Comment Period |  |  |  |  |  |
| 34. Finalize Appraisals | Appraiser |  |  |  |  |
| 35. Appraisal Reviews and Approvals | RAT |  |  |  |  |
| 36. Agreement on Values | NFP/Forest | NFP/Forest |  |  |  |
| 37. Finalize NEPA Document |  |  |  |  |  |
| 38. Draft Decision Document |  |  |  |  |  |
| 39. Finalize Certificate of Use and Consent | Zone |  |  |  |  |
| 40. Draft Exchange Agreement | Zone |  |  |  |  |
| 41. Oversight (NEPA document and supporting documents, draft decision, appraisals and reviews, draft exchange agreement, and initial file material) | RO | RO |  |  |  |
| 42. Issue Decision | Forest |  |  |  |  |
| 43. Publish Decision | Forest | NFP |  |  |  |
| 44. Appeal Period | Forest |  |  |  |  |
| 45. *Certify Estate Consistency | Zone |  |  |  |  |
| 46. Prepare Easements | Zone/NFP |  |  |  |  |
| 47. Prepare Relinquishments for Special Use Permits | Forest |  |  |  |  |
| 48. Prepare Deeds to Non-Federal Lands; Patent/ Quitclaim Deed Request Deed to Federal Lands | Zone |  |  |  |  |
| 49. Request Preliminary Title Opinion | Zone |  |  |  |  |
| 50. Provide Preliminary Title Opinion | OGC | OGC |  |  |  |
| 51. Execute Exchange Agreement | NFP/RO | NFP/RO |  |  |  |
| 52. Prepare LADS report | Zone |  |  |  |  |

| Case Name: XXXXXX Land Exchange Action Items | Responsible for Preparation | Responsible for Costs | Target Date |
| --- | --- | --- | --- |
| 53. Submit to WO for Congressional Oversight (if needed) | Zone/RO/WO |  |  |
| 54a. Record Exchange Agreement (optional) | Zone |  |  |
| 54b. Update Title Commitments (if needed) | Zone | NFP |  |
| 55. Submit Patent/Quitclaim Deed request to BLM | Zone |  |  |
| 56a. BLM issue Patent and/or Quitclaim Deed | BLM | BLM |  |
| 56b. FS issue Quitclaim Deed (if needed) | RO | RO |  |
| 57. Supplemental Certificates of Possession | Zone |  |  |
| 58. Execute Easements/Relinquishments | RO/NFP/3rd party | RO/NFP/3rd party |  |
| 59. Execute Deeds to Non-Federal Land | NFP | NFP |  |
| 60. Deliver Deeds and Patent to escrow holder | Zone |  |  |
| 61. Record Patent and All Deeds | Title Co./County |  |  |
| 62. File Water Rights Transfer/Use Documents | Zone/Forest/NFP |  |  |
| 63. Return Deeds to Non-Federal Land with Title Insurance Policy | Title Co./County | NFP |  |
| 64. Final Certificate of Use and Consent (if needed) | Zone | Zone |  |
| 65. Request Final Title Opinion | Zone | Zone |  |
| 66. Provide Final Title Opinion | OGC | OGC |  |
| 67. Finalize LADS report | Zone | Zone |  |
| 68. Send official docket (with recorded Patent and Deed) to RO | Zone | Zone |  |
| 69. Post Status and Close Case | Zone/RO | Zone/RO |  |

NFP = Non-Federal Party (XXXXXXX)

Forest = XXXXX National Forest

Zone = Regional Land Adjustment Team—XXXXX Zone

RO = Regional Land Adjustment Team—RO

RAT = Regional Appraisal Team

RMET = Regional Mineral Examiner Team

OGC = USDA Office of General Counsel

Reg. Env. Eng. = Regional Environmental Engineer

WO = Washington Office

* Certify that the estate appraised is identical to the physical estate, estate noted in Decision Document, Exchange Agreement, and Deeds.

EXHIBIT D

PROJECTED COSTS AND ALLOCATION and SPECIAL CONDITIONS

XXXXXX Land Exchange

[Revise table as needed]

| Activity/Item | Total $ | Non-Federal Party $ | USFS $ | Remarks |
| --- | --- | --- | --- | --- |
| Feasibility analysis/report | 5,000 | 500 | 4,500 | Completed |
| Property inspections | 2,000 | 500 | 1,500 | Each to pay own; partially complete |
| Publication of NOEP | 800 | 800 |  | NFP to pay provider directly |
| NEPA analysis/document preparation* | 100,000 | 100,000 |  | NFP to contract for this item and pay contractor directly |
| USFS specialist time to review NEPA (50 days x $360/day (avg)) | 18,000 | 18,000 |  | NFP to provide advance payment to USFS |
| Phase 1 Environmental Site Assessment | 10,000 | 10,000 |  | NFP to contract for this item and pay contractor directly |
| Mineral Potential Report (10 days x $450/day (avg) + $1000 travel/mileage expenses) | 5,500 | 5,500 |  | NFP to provide advance payment to USFS |
| Appraisals | 15,000 | 15,000 |  | NFP to contract for this item and pay contractor directly |
| Publish Decision | 200 | 200 |  | NFP to pay provider directly |
| Closing, Title Insurance, Escrow, Recording | 3,000 | 3,000 |  | NFP to pay title company directly |
| Case Processing ** | 25,000 |  | 25,000 | USFS salary/contract costs |
| RO Reviews *** (12 days x $450/day (avg)) | 10,000 | 5,400 | 4,600 | NFP to provide advance payment to USFS for NFP share of the costs |
| TOTALS | $194,500 | $158,900 | $35,600 |  |

(Non-Federal Party = XXXXXXXX)

[This is just one method of providing more information about the items in the table. Revise as needed.]

* Includes technical studies and investigations (wetlands, cultural survey, T&E report, etc), public involvement, agency consultation, preparation of draft and final NEPA documents.

** Includes:  Items 12-18, 22, 26f, 30, 39, 40,45, 46,48, 49, 52-55, 57, 60, 62, 64, 65, and 67-69 (as shown on Exhibit C--Implementation Schedule), and other miscellaneous/related processing needs.

*** Includes review of Feasibility Report, Agreement to Initiate, Appraisal, Phase 1 Environmental Site Assessment, NEPA document, draft decision, exchange agreement, and all related documents.

Special Conditions – XXXXX Land Exchange

1.  [Revise as needed.  If more information is required about how each of the contracts will be conducted, describe the process for each separately.]  The non-Federal party (NFP) will contract for the appraisals, Phase I Environmental Site Assessments, and NEPA analysis/document, each to be completed according to current Forest Service standards.   The Forest Service will participate with the NFP in the screening and selection of the contractor.  A qualified USFS Contracting Officer’s Representative will review and approve all contracts prior to issuance.   Each contractor will be required to provide a draft report for Forest Service review and approval.  Approval of the contract work for use in this land exchange is contingent upon Forest Service acceptance of each contractor’s work and report.

[When it is necessary to share the costs of a specific report or study, add a Special Condition defining the specific responsibilities of each party for contracting/completing the work, expected timeframes, provisions on how payment will be made, and by whom.  Show specific cost estimates in the Cost/Allocation table.]

2.  As indicated in the table above, the NFP will pay the provider/contractor directly for the following costs:  [revise list as needed]

- Publication of NOEP and decision notice

- NEPA analysis/document

- Appraisals

- Phase I Environmental Site Assessments for hazmat

- Policies of Title Insurance

- Escrow costs, recording and miscellaneous fees for closing

3.  As indicated above, the NFP will provide advance payment to the Forest Service for the following activities to be performed by Forest Service personnel: [revise list as needed]

- Specialist time to review NEPA

- Preparation of the Mineral Potential Report

- RO reviews (appraisal, Phase I ESA)

Prior to commencement of work on these activities, the U.S. Forest Service shall bill the NFP for deposits sufficient to cover the estimated costs (see Item 6 below).

4.  Billing shall be done in one single lump sum.  [-OR- specify monthly or quarterly or specific dates]

5.  Overhead costs shall be waived.

6.  Upon presentation of the Bill for Collection, the NFP will deposit with the Forest Service the amount of  [replace with proper amount]  $28,900.00 (Twenty Eight Thousand Nine Hundred Dollars and 00/100).  Supplementary deposits may be required to fund the completion of this land exchange and will be documented in mutually-approved modifications to this agreement.

7. These funds shall be available for use through                              . [insert date—if paying in one lump sum, recommend selecting a date at least several months following estimated recording to provide for likely delays]

8.  Funds collected in advance by the Forest Service, which are not spent or obligated for this land exchange, may be refunded to the NFP, authorized for use for a new agreement by the NFP, or waived by the NFP.  A DUNS number and registration in the Central Contractor Registry (CCR) by the NFP may be necessary to process a refund.  Due to processing costs, any balance less than $25 shall not be refunded to the NFP.

9.  NFP completion and/or funding of various activities associated with this land exchange does not guarantee a favorable conclusion to the NEPA process or ensure execution of the land exchange.

10.  Contact information:  [provide billing contacts for both parties; may also be helpful to add project contacts – i.e. case managers – for both parties]

| Non-Federal Party (billing contact) | U.S. Forest Service (billing contact) |
| --- | --- |
| Name: Title: Address: City, State, Zip: Telephone: FAX: Email: | Name: Title: Address: City, State, Zip: Telephone: FAX: Email: |