## Natural Resources
Name Resource Management Plan Achieving Desired Natural Resources Conditions
Plan Outcome |  | Projects/Management Actions/Tasks | PEs | Where | Priority | Magnitude | FY 12 | FY 13 | FY 14 | FY 15 | FY 16 | Cross Reference
Physical Resources | Air | Monitor air quality conditions | MI | FO wide | Medium | Moderate | 3 MI | 3 MI | 3 MI | 3 MI | 3 MI | relates to regular checks
|  | Assess projects to ensure compliance with state and federal regulations | CC |  | ND | High | 1 CC | 1 CC | 1 CC | 1 CC | 1 CC
|  | Work with air quality stakeholders to develop air quality assessment protocols | PI, PH | FO wide | ND | Medium | 1 PI | 1 PI | 1 PI | 1 PI | 1 PI | Related to # of CC
|  | Cooperate with industry and other permittees to adopt measures to reduce emissions | PH | FO wide | Medium | Low | PH | PH | PH | PH | PH
|  | Monitor air quality following prescribed fire and fuels reduction projects | MI |  | Low | Medium | 0 | 0 | 0 | 0 | 5 MI
| Water | Assess watershed conditions | BP |  |  |  | 50000 | 50000 | 50000 | 50000 | 50000
|  | Develop watershed plans | DF |  | Low | Low | 1 | 0 | 1 | 0 |  | Fish & wildlife
|  | Complete groundwater surveys | MU | Virgin River Basin | Medium | Medium | 10 | 10 | 10 | 10 | 10
|  | Map water sources and determine quantity needs and quality | BQ, BU, BV | FO wide | High | High | 20 BV | 30 BV | 20 BV | 30 BV | 20 BV
|  | Obtain and manage water rights | perennial stream areas to maintain continuous flow, Rael Property - SF river | High | low | EC |  | 1 EC
|  | Collaborate with USGS and DEQ on monitoring water quality | PI |  |  |  | PI | PI | PI | PI | PI
| Soil | Pursue & support completion of level 3 soil surveys | BO |  | Medium | High | 500 |  | 500 |  | 1000
|  | Assess soil condition | MJ, BP,BQ,BO
|  | Develop and maintain erosion & sedimentation stabilization projects | JA, JB,JC, JH | Priority watersheds: (Upper Lang's Run, Black Rock, Parashant, Lower Hurricane Valley, Fort Pearce Salinity Area, Clayhole Flood Control Structures, Wild Band Valley). | High | Medium | 4000 JA, 100 JC, 5 JH | 6000 JA, 100 JC, 6 JH | 4000 JA, 100 JC, 5 JH | 6000 JA, 100 JC, 6 JH | 6000 JA, 100 JC, 6 JH | See Veg sections
| Geological | Develop interpretive program by providing geological walk-through-time displays adjacent to the trail. | AE | La Puebla | Medium | Low
|  | Prioritize protection of sensitive formations through law enforcement patrol. | NU, NZ | Monument-wide | High | Low | [5 empty] | Law Enforce-ment
Biological Resources Biological Resources | Forests and Woodlands | Treat areas to promote forest health and restore forest stands to historic species composition, structure, and function | JB, JC | Islands, 2-Tail, McLaren, East Harlem, Barb Starr, Gold/Hunter, Rev Gulch PCT | High | High | 4000 JA, 100 JC, 5 JH | 6000 JA, 100 JC, 6 JH | 4000 JA, 100 JC, 5 JH | 6000 JA, 100 JC, 6 JH | 6000 JA, 100 JC, 6 JH
|  | Treat areas in FRCC 2 and 3 outside the WUI to transition to FRCC 1 | JQ, JR, JM | Outside the WUI | Medium | High | 800 JM, 7000 JR, 100 JQ | 800 JM, 7000 JR, 100 JQ | 800 JM, 7000 JR, 100 JQ | 800 JM, 7000 JR, 100 JQ | 800 JM, 7000 JR, 100 JQ
|  | Treat areas within the WUI to meet FRCC 1 criteria and reduce hazardous fuels | JT, JU, JW | Within the WUI | High | High | 200 JT, 50 JW, 100 JU | 100 JT, 50 JW, 200 JU | 200 JT, 50 JW, 100 JU | 100 JT, 50 JW, 200 JU | 200 JT, 50 JW, 100 JU
|  | Inventory key areas to promote forest health and restore forest stands to historic species composition, structure, and function | BT | CDA small sales, Murray, Mullan South, Wallace South | High | High | 200 BT | 100 BT | 300 BT | 200 BT | 100 BT
|  | Monitor the effectiveness of completed fuels treatments | MT |  | Medium | Moderate | 8000 MT | 10000 MT | 8000 MT | 8000 MT | 8000 MT
| Grasslands and Shrublands | Complete Land Health Assessments | MJ |  | High |  | 30 MJ | 40 MJ | 30 MJ | 40 MJ | 30 MJ
|  | Maintain native and desirable nonnative plant communities in nonforested areas | MX, JA, JB, JC | FO wide | High | Moderate | 5000 JA, 6 JB, 4 JC, 10,000 MX | 6000 JA, 4 JB, 5 JC, 8000 MX | 7000 JA, 5 JB, 6 JC, 7000 MX | 6000 JA, 4 JB, 5 JC, 8000 MX | 5000 JA, 6 JB, 4 JC, 10,000 MX
|  | Initiate Native Seed Collection Program | JZ |  | Low
|  | Coordinate with adjacent landowners, agencies, tribes, individuals, communities, and municipalities to meet beneficial use criteria | AL | FO wide | Medium | Low | 10 AL | 10 AL | 10 AL | 10 AL | 10 AL
| Riparian/Wetlands | Complete Watershed Management Plans | DF | Area wide | Medium | Moderate |  | 1 DF | 2DF |  |  | Fish & Wildlife
|  | Complete Land Health Assessments | MJ |  | ND |  | 2 MJ | 2 MJ | 2 MJ | 2 MJ | 2 MJ
|  | Conduct PFC Assessments | BP |  | High | Moderate | 10000 BP | 8000 BP | 7000 BP | 10000 BP | 9000 BP
|  | Construct and maintain riparian treatments | JG, JA, JH, JI, PH | Largo Wash Improvement Project, Simon Riparian Improvement Project, Lamanga Watershed Restoration Project, San Juan River Stabilization Project |  |  | 10 JG, 5 JH, 9 JI | 11 JG, 5 JH, 9 JI | 12 JG, 5 JH, 9 JI | 12 JG, 5 JH, 9 JI | 12 JG, 5 JH, 9 JI
|  | Monitor effectiveness within the Riparian Monitoring Plan: PFC evaluation, photo points | MO | SF river, Orilla Verde, Rio grande, ojo caliente, all riparian areas | High | Medium | 30 MO | 30 MO | 30 MO | 30 MO | 30 MO
|  | Partner with YCC, SJSWCD, NRCS, San Juan County External Office | PH | Area wide | Medium | High | PH | PH | PH | PH | PH
| Invasive/ Non-native Species | Inventory and map invasive non-native species in planning | BS | FO wide | Medium | High | 500 BS | 200 BS | 300 BS | 300 BS | 300 BS
|  | Develop cooperative weed management plans | DF | FO wide | Low | Medium |  |  |  | 1 DF
|  | Apply weed treatments | JD | Recreation sites | Medium | Low | 10 JD | 20 JD | 10 JD | 15 JD | 10 JD
|  | Monitor treatment effectiveness and non-native spread and distribution around ROWs and permitted activities | MK | FO wide | Medium | Low | 50 MK | 50 MK | 50 MK | 50 MK | 50 MK
| Fish and Wildlife | Assess and monitor aspen key habitats | MQ, MR, CB | FO wide | Medium | Medium | 50000 MQ, 10 MR, 10000 CB
|  | Develop habitat management plan for big game winter habitat | DF | FO wide | Medium | Medium |  |  | 1 DF
|  | Assess historic and suitable habitat for introductions/reintroductions of native or naturalized fish and wildlife species | CB |  | Low |  |  |  | 600 CB
|  | Coordinate and consult with USFWS and NMFS (section 7); collaborate and cooperate with federal, state, and tribal governments; private entities; watershed councils; and weed management groups | FO wide | ND for sec. 7 consultation
|  | Maintain treatments, fences, wildlife waters | FO wide | high |  | JC | 125 JC | 125 JC | 125 JC | 125 JC | 125 JC
|  | Complete habitat management plans | DK, DF | FO wide | Medium | High | 1 DF | 1 DF
|  | Plan and implement reintroduction of prairie dogs | DF, KE, MR | San Pedro ACEC | Medium | High |  | 1 KE
|  | Complete fish habitat quality and quantity surveys on all streams within the Field Office on a 10 year rotating cycle | BN, CB,BV |  | Medium |  | 12 BN, 10 BV | 12 BN, 10 BV | 12 BN, 10 BV | 12 BN, 10 BV | 12 BN, 10 BV
|  | Coordinate with affected interests, permittees, and state and local agencies and partners | PI | FO wide | High | Medium | PI | PI | PI | PI | PI
| Special Status Species | Develop and implement an inventory & monitoring program for special status species (SS-2) | CB | FO wide | High | Low |  | 500 CB |  | 500 CB
|  | Partner with state game and fish agencies, US Fish & Wildlife Service, and other wildlife services on recovery plans | DK, JP | FO wide | Low | Medium | 3 JP | 3 JP | 3 JP | 3 JP | 3 JP
|  | Monitor and survey species populations | MQ, MR, | FO wide | High | Low | 3 MR, 4000 MQ | 3 MR, 4000 MQ | 3 MR, 4000 MQ | 3 MR, 4000 MQ | 3 MR, 4000 MQ
|  | Participate in ongoing interagency efforts to identify, map and manage linkage habitats essential to grizzly bear movement between ecosystems | MQ, MR, PI | FO Wide |  |  | PI | PI | PI | PI | PI
|  | Reintroduce desert bighorn sheep | DK, JP | Devil's Backbone | High | Moderate |  | DK | 2 JP

## Heritage Resources
Name Resource Management Plan Achieving Desired Heritage Resources Conditions
Plan Outcome |  | Projects/Management Actions/Tasks | PEs | Where | Priority | Magnitude | FY 12 | FY 13 | FY 14 | FY 15 | FY 16 | Cross Reference
Cultural/ Paleontological Resources | Cultural Resources | Conduct Section 106 compliance/program support | BC | FO Wide | ND | Moderate | 500 BC | 500 BC | 500 BC | 500 BC | 500 BC
|  | Conduct proactive inventory of cultural resources on at least 200 acres/year identified as high potential | BC, FD |  | High | Moderate | 200 CD, 10 FD | 200 CD, 10 FD | 200 CD, 10 FD | 200 CD, 10 FD | 200 CD, 10 FD
|  | Stabilize/protect areas identified as NRHP eligible | HF, MY |  | Medium |  | 8 HF, 20 MY | 8 HF, 20 MY | 8 HF, 20 MY | 8 HF, 20 MY | 8 HF, 20 MY
|  | Administer/monitor contracts to collect cultural resource information. | FB |  | ND |  | 1 FB | 1 FB | 1 FB | 1 FB | 1 FB
|  | Conduct education and outreach/cooperative agreements with community groups | AE, AL |  | Medium | Low | 60 AL | 10 AE, 60 AL | 5 AE, 60 AL | 60 AL | 60 AL
|  | Develop field school opportunities and coordinate projects (Columbia University, Metro State) | Rio Grande Gorge, Cerro de la Olla | high | medium | BC, FD
|  | Complete Kane Creek CMA | DC |  | Medium |  |  |  | DC
|  | Maintain cultural interpretive sites | AL | Sego, Wall Street | Low |  |  | 1 AL |  | 1 AL
|  | Consult with tribes to determine high priority inventory areas | AJ |  |  |  | 5 AJ | 5 AJ | 5 AJ | 5 AJ | 5 AJ
|  | Cooperate with Site Watch volunteers | MY, PC |  |  |  | 30 MY | 30 MY | 30 MY | 30 MY | 30 MY
| Paleontological Resources | Locate and evaluate paleontological resources | BC |  | Medium | Moderate | 100 BC | 100 BC | 100 BC | 100 BC | 100 BC
|  | Develop signs and pamphlets for public visitation of paleo sites, especially in the Dinosaur Diamond. | AE, AL |  | Low | Moderate
|  | Permit scientific research | FB |  | ND |  | 1 FB |  | 1 FB |  | 1 FB
Special Designations | Madhya ACEC | Complete ACEC management plan | DF |  | High | High | DF
|  | Construct grazing exclosures | IY |  | Medium | High |  |  | 1 IY
|  | Recommend for withdrawal | ET |  | High |  |  | ET
|  | Manage the riparian areas to return them to full functioning condition, restore native plant species, and reduce the density and control the spread of exotic vegetation | BS, JG, JH, JI, MO |  | High | High | 1200 BS | 1200 JG | 1200 JI | 1200 MO
| Chama Canyons ACEC (significant riparian, wildlife, water quality, and scenic resources.) | Evaluate areas for introduction, augmentation or reestablishment of fish and wildlife species consistent with state Department of Game and Fish (NMDGF) plans | BN, CB, BQ |  | Low | Moderate
|  | Monitor habitat critical for winter range and migration for elk and mule deer | MR |  | Medium |  | 2000 MR | 2000 MR | 2000 MR | 2000 MR
|  | Restore native aquatic fauna and reduce or eliminate aquatic invasive species in cooperation with NMDGF | JG, JH, JI, MO |  | Medium |  |  | 4000 JG
|  | Acquire available private land with trail resources by purchase or exchange | FM, FO |  | High | High |  | 700 FM, 700 FO
|  | secure water rights in perennial streams adequate to manage aquatic habitat and riparian vegetation | EC |  | Medium | High |  | EC
|  | Manage Rio Chama in-stream hydrologic processes to maximize aquatic and riparian habitat area and condition, and reduce excessive deposition of erosion | BP, BV |  | High | High | 12 BP, 1 BV | 12 BP, 1 BV | 12 BP, 1 BV | 12 BP, 1 BV | 12 BP, 1 BV
| Wildness and Wilderness Study Areas (WSAs) | Develop Wilderness Management Plans | DC |  | High | High | DC
|  | Monitor wilderness characteristics | MD |  | High | Low | 40000 MD | 40001 MD | 40002 MD | 40003 MD | 40004 MD
|  | Develop signage | IU |  | Low | Low |  | 2 IU
|  | Maintain wilderness character inventory | BE |  | ND | Moderate
| Wild Horse & Burros | Update management plans based upon monitoring data Fly Census Herd Management Areas | MC |  | High | High | MC | MC | MC | MC | MC
|  | Develop wild horse management plans where needed | DI |  | Low
|  | Conduct horse removal as needed to meet AML for each Herd Management Area. | JJ | [6 empty] | 150 JJ
|  | Response to public requests for wild horse information (compliance of adopted horses) | NK
|  | Monitor Herd Management Areas to determine if RMP goals and objectives are being attained | MP |  | Medium | Low | 1 MP | 1 MP | 1 MP | 1 MP | 1 MP
| Wild and Scenic Rivers | Develop WSR management plan | DC |  | Low | High
|  | Monitor WSR conditions | MF |  | Medium |  | 100 MF | 101 MF | 102 MF | 103 MF | 104 MF
National Historic Trails
| El Camino Real de Tierra Adentro National Historic Trail | Acquire available private land with trail resources by purchase or exchange | FM, FO |  | Medium | High |  |  | 100 FO, 100 FM
|  | Inventory and record trail resources in detail (class III) | FD |  | Medium | High |  | 1 FD |  | 1 FD
|  | Nominate eligible cultural sites to the National Register of Historic Places |  |  | Medium | Moderate |  |  | X
|  | Protect trail segments and associated archaeological sites | HF |  | High | High | 1 HF | 1 HF | 1 HF | 1 HF | 1 HF
|  | Develop interpretation and education projects where appropriate | AE, AL |  | Low |  |  |  |  | 1 AL
|  | Monitor site condition using site stewards and BLM staff | MY |  | High | Moderate | 1 MY | 1 MY | 1 MY | 1 MY | 1 MY

## Energy and Minerals
Name Resource Management Plan Achieving Desired Energy and Minerals Conditions
Plan Outcome |  | Projects/Management Actions/Tasks | PEs | Where | Priority | Magnitude | FY 12 | FY 13 | FY 14 | FY 15 | FY 16 | Cross Reference
Energy Resources | Oil & Gas | Inventory potential lease parcels for resource concerns | B codes |  | ND | High
|  | Develop and issue federal fluid mineral leases | EI |  | ND | High | 20 EI | 20 EI | 20 EI | 20 EI | 20 EI
|  | Process, inspect, and monitor geophysical exploration permits | FT |  | ND | Low | 1 FT | 1 FT | 1 FT | 1 FT | 1 FT
|  | Complete POD EIS for Blackcherry Creek | DF |  | ND | High |  | DF
|  | Process fluid minerals APDs | EJ |  | ND | High | 80 EJ
|  | Develop Unitization Agreements | FF |  | ND | High | 40 FF | 40 FF | 40 FF | 40 FF | 40 FF
|  | Process sundry notices | FJ |  | ND | Low | 800 FJ | 800 FJ | 800 FJ | 800 FJ | 800 FJ
|  | Conduct I&E/surface compliance | NB, NH |  | ND | Moderate | 500 NB | 500 NB | 500 NB | 500 NB | 500 NB
|  | Coordinate with surface management agencies, tribes, and landowners to minimize impacts of fluid mineral development |  |  | High
|  | Monitor effectiveness of stipulations and COAs | MW |  | High | Moderate | 100 MW | 100 MW | 100 MW | 100 MW | 100 MW
| Coal | Process coal leases and exploration licenses | EL |  | ND | High | 1 EL | 2 EL
|  | Process mining plans of operation | EX |  | ND | High | 1 EX | 2 EX
|  | Inspect coal operations and verify production | NG |  | High | Moderate | 40 NG | 40 NG | 40 NG | 40 NG | 40 NG
|  | Inventory potential lease parcels for resource concerns | B codes |  | High | Moderate | 1 | 2
|  | Monitor effectiveness of stipulations and COAs | M codes |  | medium | Moderate |  | 1 | 2
| Oil Shale & Tar Sands | Inventory potential lease parcels for resource concerns | B codes
|  | Complete OSEC mine plan | EX |  | ND | High | 1 EX
|  | Complete preference right leases | EL |  | ND | High
|  | Conduct compliance inspections for compliance with the mine plan | NG, NB |  | High | High |  | 1 NG 1 NB | 1 NG 1 NB | 1 NG 1 NB | 1 NG 1 NB
|  | Complete yearly reclamation report | PP |  | Medium | High |  | PP | PP | PP | PP
|  | Monitor effectiveness of stipulations and COAs | M codes |  | Medium | Moderate |  | 1 | 1 | 1 | 1
| Renewable Energy Resources | Process ROW applications for wind and solar energy projects | FX |  | ND | High | 1 FX | 2 FX | 3 FX | 1 FX | 1 FX
|  | Conduct renewable energy (wind/solar) compliance | OD |  | ND | High | 2 OD | 3 OD | 4 OD | 4 OD | 4 OD
|  | Inventory potential lease parcels for resource concerns | B codes |  | ND | High | 1 | 2 | 3 | 1 | 1
|  | Monitor effectiveness of stipulations and COAs | M codes |  | ND | High | 2 | 3 | 4 | 4 | 4
Mineral Resources | Locatable | Inventory potential lease parcels for resource concerns | B codes |  |  |  | 4 | 4 | 4 | 4 | 4
|  | Determine mining claim validity and process mineral applications | EY
|  | Process mining notices | FL |  | ND | High | 4 FL | 4 FL | 4 FL | 4 FL | 4 FL
|  | Process cost recovery mining law administration, validity and mineral examinations | GN
|  | Conduct inspection and enforcement | NI |  | High | Moderate | 20 NI | 20 NI | 20 NI | 20 NI | 20 NI
|  | Monitor effectiveness of stipulations and COAs | M codes |  | Medium | Moderate | 20 | 20 | 20 | 20 | 20
| Salable | Inventory potential lease parcels for resource concerns | B codes |  |  |  | 40 | 40 | 40 | 40 | 40
|  | Process mineral material applications | EP, FW |  | ND | High | 40 EP, 6 FW | 40 EP, 6 FW | 40 EP, 6 FW | 40 EP, 6 FW | 40 EP, 6 FW
|  | Process cost-recovery mineral materials (competitive sale) | GL |  |  |  | 1 GL |  | 1 GL |  | 1 GL
|  | Process cost recovery mineral materials (contract renewal) | GM |  |  |  | 1 GM |  | 1 GM |  | 1 GM
|  | Conduct inspection and enforcement | OB, NI |  | High | Moderate | 80 NI, 30 OB | 90 NI,40 OB | 80 NI, 30 OB | 90 NI,40 OB | 80 NI, 30 OB
|  | Monitor effectiveness of stipulations and COAs | M codes
| Leasable (Potash) | Inventory potential lease parcels for resource concerns | B codes |  |  |  | 1
|  | Process and authorize competitive sales | EL |  |  |  | 1 EL | 2 EL
|  | Process pit development plan and reclamation plan | EX |  |  |  |  | 1 EX | 2 EX
|  | Monitor effectiveness of stipulations and COAs | M codes |  |  |  | 1 | 1 | 1

## Forest Products & Livestock Mgt
Name Resource Management Plan Achieving Desired Forest Products & Livestock Mgt Conditions
Plan Outcome |  | Projects/Management Actions/Tasks | PEs | Where | Priority | Magnitude | FY 12 | FY 13 | FY 14 | FY 15 | FY 16 | Cross Reference
Livestock Management | Enhancing Livestock Management | Evaluate standards for rangeland health on individual allotments | MJ |  | High | Moderate | 40 MJ | 40 MJ | 40 MJ | 40 MJ | 40 MJ
|  | Issue, renew or modify grazing permits | EE |  | ND | High | 80 EE | 80 EE | 80 EE | 80 EE | 80 EE
|  | Process transfers of permits | ED |  | ND | Moderate | 10 ED | 10 ED | 10 ED | 10 ED | 10 ED
|  | Complete allotment management plans | DF
|  | Monitor allotments to ensure standards are being met | ML |  | High | Moderate | 40 ML | 40 ML | 40 ML | 40 ML | 40 ML
|  | Inspect allotments for compliance with permits | NA |  | High | Moderate | 60 NA | 60 NA | 60 NA | 60 NA | 60 NA
Forest Products | Commercial sales | Identify areas available for commercial sales | HL, BT |  | Medium | Moderate | 201 BT, 100 HL | 200 BT, 100 HL | 201 BT, 100 HL | 200 BT, 100 HL | 200 BT, 100 HL
|  | Prepare vegetative permits and contracts | EG |  |  |  | 200 EG | 200 EG | 200 EG | 200 EG | 200 EG
|  | Process sales and permits | HD, JE, JN |  | ND | Moderate | 100 HE, 100 JN | 50 HE, 75 JE | 100 HE, 100 JN | 100 HE, 100 JN | 100 HE, 100 JN
|  | Monitor sales/stand health | MB |  | Medium | Moderate | 20000 MB | 20000 MB | 20000 MB | 20000 MB | 20000 MB
| Vegetative sales | Inventory areas available for veg sales | BT |  | Low
|  | Prepare vegetative permits/contracts | EG |  | ND | Moderate | 300 EG | 300 EG | 300 EG | 300 EG | 300 EG
|  | Monitor sales/stand health | MB |  | Medium | Moderate | 4000 MB | 4000 MB | 4000 MB | 4000 MB | 4000 MB

## Recreation and Travel
Name Resource Management Plan Achieving Desired Recreation and Travel Conditions
Plan Outcome |  | Projects/Management Actions/Tasks | PEs | Where | Priority | Magnitude | FY 12 | FY 13 | FY 14 | FY 15 | FY 16 | Cross Reference
Recreation | SRMA 1 - Insert name and add rows as necessary for each SRMA | Conduct periodic condition and trend assessment | BA, MA, MV |  | Medium | Moderate | 3000 BA, 200 MA, 20 MV |  | 3000 BA, 200 MA, 20 MV |  | 3000 BA, 200 MA, 20 MV
|  | Develop SRMA management plan | DA |  | High | High |  | DA
|  | Construct and maintain interpretive trail | GY, IE, ID |  | Medium | High |  |  | 10 GY | 10 ID | 10 ID
|  | Conduct regular patrols and visitor contacts. | MA, NU |  | High | Low | 3000 MA, 5 NU | 3000 MA, 5 NU | 3000 MA, 5 NU | 3000 MA, 5 NU | 3000 MA, 5 NU
|  | Provide, update, and maintain information | AL |  | Low
Close to shooting
|  | Obtain easements for trail connections in Copper Hill zone | FO
|  | Issue, manage and monitor SRPs | EA, EB, FH |  | ND | High | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH
| SRMA 2 - Insert name and add rows as necessary for each SRMA | Conduct periodic condition and trend assessment | BA, MA, MV |  | Medium | Moderate |  | 6000 BA, 400 MA, 10 MV |  | 6000 BA, 400 MA, 10 MV
|  | Issue, manage and monitor SRPs | EA, EB, FH |  | ND | High | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH
|  | Update brochures and maps | AL |  | Medium | Moderate |  | 1 AL
|  | Maintain existing facilities | IU |  | High | Moderate | 4 IU | 4 IU | 4 IU | 4 IU | 4 IU
|  | Maintain access road | IP |  | Medium | Moderate |  |  | 4 IP
|  | Conduct Regular patrols and visitor contacts. | MA, NU |  | Medium | Moderate | 3000 MA, 5 NU | 3000 MA, 5 NU | 3000 MA, 5 NU | 3000 MA, 5 NU | 3000 MA, 5 NU
|  | Revise activity plan | DA |  | Medium |  |  |  | DA
| ERMA 1 - Insert name and add rows as necessary for each ERMA | Conduct periodic condition and trend assessment | BA, MA, MV | [5 empty] | 10000 BA, 400 MA, 10 MV
|  | Issue, manage and monitor SRPs | EA, EB, FH |  |  |  | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH | 2 EA, 2 EB, 3 FH
| Area-wide | Conduct periodic condition and trend assessment | BA, MA, MV |  | Low | Moderate
|  | Issue, manage and monitor SRPs | EA, EB, FH |  | ND | High | 50 EA, 9000 EB, 100 FH | 50 EA, 9000 EB, 100 FH | 50 EA, 9000 EB, 100 FH | 50 EA, 9000 EB, 100 FH | 50 EA, 9000 EB, 100 FH
|  | Cooperate with RAC and other interest groups to identify opportunities for recreation | PM |  | High | Moderate | PM | PM | PM | PM | PM
Travel | Management | Develop maps of trail/road network | AL |  | Low | High
|  | Inventory existing roads and trails | BY, MV |  | High | High | 300 BY | 500 BY |  | 600 BY
|  | Develop travel management plan | DA |  | Medium | High |  |  | DA |  | DA
|  | Close non-designated roads | JX |  | High | High | 100 JX |  |  | 200 JX
|  | Rehabilitate roads in closed areas | JX |  | Medium | High |  | 10 JX |  |  | 10 JX
|  | Monitor road network conditions | MV |  | Medium | Moderate | 200 MV | 200 MV | 200 MV | 200 MV | 200 MV
|  | Maintain roads/trails as necessary based on monitoring results | ID, IE, IP, IQ |  | High | High | 30 ID, 30 IP, 6 IE, | 30 ID, 30 IP, 6 IE, | 30 ID, 30 IP, 6 IE, | 30 ID, 30 IP, 6 IE, | 30 ID, 30 IP, 6 IE,
|  | Develop partnerships to develop travel network and maintain roads | PM, PN |  | High | Moderate | PM, PN | PM, PN | PM, PN | PM, PN | PM, PN
| Facilities | Maintain dam at Fort Ojito site | IJ |  |  |  | 1 IJ |  | 1 IJ |  | 1 IJ
|  | Monitor dam at Fort Ojito site | GW |  |  |  |  | 1 GW |  | 1 GW

## Direct Community Services
Name Resource Management Plan Achieving Desired Direct Community Services Conditions
Plan Outcome |  | Projects/Management Actions/Tasks | PEs | Where | Priority | Magnitude | FY 12 | FY 13 | FY 14 | FY 15 | FY 16 | Cross Reference
Fire Management | Wildfire Management | Identify hazardous fire conditions/fuel loads and associated FRCC class | HT, BT | FO Wide | High | Low | 200 BT | 200 BT | 200 BT | 200 BT | 200 BT
|  | Maintain and revise Fire Management Plan (FMP) and Community Wildfire Protection Plan | DF | FO Wide | Low | Low | [6 empty] | 779
|  | Implement fuels reduction projects by mechanical, chemical and prescribed fire projects | HT,JW,JT, JU,JM,JQ, JR | FO Wide | Medium | High | 800 JM, 200 JQ, 10000 JR, 500 JT, 200 JW | 800 JM, 200 JQ, 10000 JR, 500 JT, 200 JW | 800 JM, 200 JQ, 10000 JR, 500 JT, 200 JW | 800 JM, 200 JQ, 10000 JR, 500 JT, 200 JW | 800 JM, 200 JQ, 10000 JR, 500 JT, 200 JW | See veg sections | 200
|  | Complete burn plans | DF | Cyprian, Gallatin Rapids, Wood Bottom | Medium | Moderate |  | 2 DF |  | 1 DF |  |  | 10000
|  | Provide rural fire and community assistance | AM |  | Medium | Moderate | AM | AM | AM | AM | AM |  | 0
|  | Manage wildland fire consistent with policy and fire management plan | HU |  | High | High | [6 empty] | 2000
|  | Monitor effectiveness of fires for resource benefit | MT |  |  |  | 6000 MT | 6000 MT | 6000 MT | 6000 MT | 6000 MT
|  | Stabilize/rehabilitate burned areas consistent with FMP | JS, JL, MZ |  |  |  | 2000 JL | 2000 JL | 2000 JL | 2000 JL | 2000 JL
|  | Work with partners in the WUI for fire management (local fire departments, county fire wardens) | HT, PN | FO Wide | Medium | Medium | HT, PN | HT, PN | HT, PN | HT, PN | HT, PN
Access (Realty) | Land Tenure | Complete PN Ranch land exchange | FM | PN Ranch | High | High |  |  | 4000 FM
|  | Acquire lands and maintain easements across non-BLM lands to support resource programs | HN, FM | FO Wide | Medium | Medium | 1000 FM, 2000 FO | 30 HN |  | 1800 FO, 2000 FO
|  | Initiate land disposals of scattered parcels in Northwest Planning Unit | EU |  | Medium | High |  | 10 EU | 10 EU |  | 10 EU
|  | Acquire Judith Landing (campground and landing) | HN | Blaine, Phillips, and Fergus | High | High |  |  | 20 HN
|  | Process R&PP lease with the city | ES |  | ND |  |  | 1 ES
|  | Pursue opportunities for land exchanges with the Dept of Natural Resources and Conservation | FO, FM | FO Wide | Low | High
|  | Acquire new site for boat ramp | EQ | Coal Banks | Medium | Medium |  |  | 1 IQ
| Land Use (ROWs) | Process withdrawal actions | ET | FO Wide | Medium | Low |  | 20,000 ET |  | 40,000 ET
|  | Issue and process new ROWs | ER, FP | FO Wide | High | High | 15 ER, 5 FP | 15 ER, 5 FP | 15 ER, 5 FP | 15 ER, 5 FP | 15 ER, 5 FP
|  | Conduct compliance and inspection on ROWs | NH |  | Medium | Low | 20 NH | 20 NH | 20 NH | 20 NH | 20 NH
|  | Monitor effectiveness of mitigation measures | M codes |  | Medium | Medium | 20 | 20 | 20 | 20 | 20
| Unauthorized Use | Resolve trespass (dumping, grazing, occupancy, agricultural, illegal collection, etc.) | NJ | FO Wide | High | High | 2 NJ | 2 NJ | 2 NJ | 2 NJ | 2 NJ
|  | Educate public on illegal uses of public land | AL | Bosque | Medium | Medium |  | AL
|  | Use volunteers to clean up illegal dumping | PN | FO Wide | Medium | Low | PN | PN | PN | PN | PN
Public Safety | Law Enforcement | Complete law enforcement plan | DD | FO Wide | Low | Medium |  |  |  | 1 DD
|  | Provide law enforcement ranger & river ranger patrols | DD | Area wide | High | Medium
|  | Conduct drug enforcement activities | OA
|  | Conduct patrol enforcement activities | NU, DD |  | High | Medium | 13 NU | 13 NU | 13 NU | 13 NU | 13 NU
|  | Conduct non drug investigation activities | NV |  | High | Medium | 10 NV | 10 NV | 10 NV | 10 NV | 10 NV
|  | Investigate trespass | NU |  | High | High | 1 NU | 1 NU | 1 NU | 1 NU | 1 NU
|  | Conduct emergency response activities | NY |  | High | High | 5 NY | 5 NY | 5 NY | 5 NY | 5 NY
|  | Assist counties with search and rescue as requested | DD | Blaine, Chouteau, Fergus, and Phillips counties | High | Low
| Hazardous Waste | Identify physical (human, property) hazards | BF, BG | FO Wide | High | Low | 3 BF, 3 BG | 3 BF, 3 BG | 3 BF, 3 BG | 3 BF, 3 BG | 3 BF, 3 BG
|  | Respond to hazmat emergencies | HO, NY |  |  |  | 2 HO, 1 NY | 2 HO, 1 NY | 2 HO, 1 NY | 2 HO, 1 NY | 2 HO, 1 NY
|  | Monitor and maintain remediation sites | MG | FO Wide | Low | Medium |  | 6 MG |  | 3 MG
| Abandoned Mine Lands | Inventory AML sites | BH |  | High | Moderate | 2 BH |  | 2 BH
|  | Remediate AML sites | HP,JK |  | High | High |  | 2 HP, 10 JK |  | 2 HP, 10 JK
|  | Monitor effectiveness of remediation | MG |  | Medium | Moderate |  |  | 2 MG |  | 2 MG
|  | Maintain remediation sites | MG |  | Medium | High |  |  |  | 2 MG